## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | NEXA The Travel Booking Platform |  |  |  |  | COMPANY NAME | [6 empty] | Arcade Nation
PROJECT MANAGER | [6 empty] | DATE | [6 empty] | 2025-11-13
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE |  |  |  |  | PHASE TWO | [9 empty] | PHASE THREE | [11 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Planning
1.1 | Requirements Design | Likith | 2025-09-13 | 2025-09-18 | 5 | 100% | bar: WEEK 1 F
1.1.1 | System Design | Rohit | 2025-09-13 | 2025-09-18 | 5 | 100%
1.2 | Technology Stack Identification | Aman | 2025-09-13 | 2025-09-18 | 5 | 90%
1.3 | Documentation | Karthik | 2025-09-13 | 2025-09-18 | 5 | 100% | bar: WEEK 1 F
2 | Resource Identification
2.1 | Hosting Backend | Likith | 2025-09-18 | 2025-09-30 | 12 | 100% | bar: WEEK 2 M; WEEK 4 M to WEEK 4 R
2.2 | Hosting Front End | Karthik | 2025-09-18 | 2025-09-30 | 12 | 100% | bar: WEEK 2 M to WEEK 2 T; WEEK 4 F to WEEK 5 F
2.3 | LLM calls and Stack Discovery | Rohit | 2025-09-18 | 2025-09-30 | 12 | 100% | bar: WEEK 2 T to WEEK 2 W
3 | Project Code Implementation
3.1 | FrontEnd UI/UX | Karthik | 2025-09-30 | 2025-10-12 | 12 | 100%
3.2 | Backend Auth and Utilities Logic | Likith | 2025-09-30 | 2025-10-12 | 12 | 80%
3.2.1 | Core Utilities Implementation Backend | Rohit | 2025-09-30 | 2025-10-12 | 12 | 80%
3.2.2 | Auth Support | Rithwin | 2025-09-30 | 2025-10-12 | 12 | 40%
3.3 | Admin UI Integration | Ritesh | 2025-09-30 | 2025-10-12 | 12 | 50%
4 | Testing and Improvements
4.1 | Core Functionalities | Likith | 2025-10-12 | 2025-11-12 | 30 | 80%
4.2 | Auth and Utilities | Rohit | 2025-10-12 | 2025-11-12 | 30 | 80%
4.3 | UI Integration | Karthik | 2025-10-12 | 2025-11-12 | 30 | 90%
4.4 | UI Integration Debugging | Likith | 2025-10-12 | 2025-11-12 | 30 | 70%